## SQL UPGRADE CHECKLIST
SQL UPGRADE CHECKLIST (CSV)
Step | Category | Task | Expected Result | Actual Result | Pass/Fail | Notes
Pre‑Checks | Run Pre‑Upgrade Scan | No warnings or only acceptable warnings
Pre‑Checks | Run Driver Scan | No incompatible filter drivers
Pre‑Checks | Check Pending Reboot | No reboot pending
Pre‑Checks | Check Disk Space | Enough free space for in‑place upgrade
Pre‑Checks | Verify SQL Backups | All DBs backed up successfully
Pre‑Checks | Verify SQL Agent Jobs | All critical jobs succeeded
Pre‑Flight | Run PreFlightBackup.ps1 | Backup folder created with certs | RDS (if any) | IIS | logs
Snapshot | Create Hyper‑V Snapshot | Snapshot created successfully
Upgrade | Run Server 2025 Setup | Upgrade completes with no errors
Post‑Upgrade | Run PostUpgradeRestore.ps1 | Certs restored | RDS licensing restored (if present)
Post‑Upgrade | Check SQL Services | SQL services running normally
Post‑Upgrade | Run DBCC CHECKDB | No corruption detected
Post‑Upgrade | Test Application Connectivity | Apps connect to SQL successfully
Defender | Install Defender MSI | AV + EDR installed
Defender | Run DefenderHealthScore.ps1 | Score ≥ 4/5
Hardening | Run Hardening2025.ps1 | Settings applied successfully
Validation | Check Event Logs | No critical errors
Validation | Verify Backups Resume | Backup jobs run successfully
Validation | Remove Snapshot (optional) | Snapshot removed after validation

## RDS UPGRADE CHECKLIST
SHEET 2 — RDS UPGRADE CHECKLIST (CSV)
Step | Category | Task | Expected Result | Actual Result | Pass/Fail | Notes
1 | Pre‑Checks | Run Pre‑Upgrade Scan | No warnings or only acceptable warnings
2 | Pre‑Checks | Run Driver Scan | No incompatible filter drivers
3 | Pre‑Checks | Check Pending Reboot | No reboot pending
4 | Pre‑Checks | Check Disk Space | Enough free space for in‑place upgrade
5 | Pre‑Flight | Run PreFlightBackup.ps1 | Backup folder created with certs | RDS deployment | RDS licensing | IIS
6 | Snapshot | Create Hyper‑V Snapshot | Snapshot created successfully
7 | Upgrade | Run Server 2025 Setup | Upgrade completes with no errors
8 | Post‑Upgrade | Run PostUpgradeRestore.ps1 | Certs restored | RDS licensing restored
9 | RDS | Check Connection Broker | CB service healthy
10 | RDS | Check Session Host | Sessions accepted
11 | RDS | Check RDWeb | RDWeb loads successfully
12 | RDS | Check RD Gateway (if used) | Gateway accepts connections
13 | RDS | Check Licensing | Server issues CALs
14 | RDS | Check FSLogix (if used) | Profiles mount/unmount cleanly
15 | Defender | Install Defender MSI | AV + EDR installed
16 | Defender | Run DefenderHealthScore.ps1 | Score ≥ 4/5
17 | Hardening | Run Hardening2025.ps1 | Settings applied successfully
18 | Validation | Test User Login | User can log in via RDS
19 | Validation | Check Event Logs | No critical RDS/TerminalServices errors
20 | Validation | Remove Snapshot (optional) | Snapshot removed after validation

## DEFENDER + HARDENING VALIDATION
DEFENDER + HARDENING VALIDATION (CSV)
Step | Category | Task | Expected Result | Actual Result | Pass/Fail | Notes
1 | Defender | Verify WinDefend Service | Running
2 | Defender | Verify Sense Service | Running
3 | Defender | Check Platform Folder | Latest platform version present
4 | Defender | Check Signature Age | Updated within 7 days
5 | Defender | Check Cloud Connectivity | Outbound 443 OK
6 | Defender | Check Defender Events | Operational events present
7 | Defender | Run DefenderHealthScore.ps1 | Score ≥ 4/5
8 | Hardening | Check TLS Settings | TLS 1.2 enabled | 1.0/1.1 disabled
9 | Hardening | Check SMBv1 | Disabled
10 | Hardening | Check RDP NLA | Enabled
11 | Hardening | Check ASR Rules | ASR rules in audit mode
12 | Hardening | Check Network Protection | Enabled
13 | Hardening | Check MAPS/Cloud Protection | Enabled
14 | Validation | Check Event Logs | No critical security errors

## DC DEMOTION READINESS
DC DEMOTION READINESS
Step | Category | Task | Expected Result | Actual Result | Pass/Fail | Notes
1 | FSMO | Check FSMO Roles | All FSMO roles on DC25
2 | Global Catalog | Check GC Servers | DC25 listed as GC
3 | Replication | Run repadmin /replsummary | No fails | no high latency
4 | DNS | Run dcdiag /test:DNS | All tests pass
5 | SYSVOL | Run dcdiag /test:SYSVOLCHECK | SYSVOL healthy
6 | Domain Controllers | List DCs | Only DC25 + old DC
7 | DNS Clients | Check DNS Settings | All servers/clients use DC25 as primary
8 | Health | Check Event Logs | No AD/DNS/SYSVOL critical errors
9 | Final | Check Backup of Old DC | Backup exists before demotion
10 | Demotion | Run dcpromo / demote | Completes successfully
11 | Cleanup | Remove old DC from Sites & Services | Old DC removed
12 | Cleanup | Remove old DC DNS records | Records removed
13 | Cleanup | Remove old DC computer object | Object removed